## Sheet1
Date | Start time | End time | Hours | Reason | Total time (hours): | 88.5833
2016-01-27 | 10:30 | 11:30 | 1 | Discussing which project to work on with Chris (site lead)
2016-01-28 | 10:30 | 12:00 | 1.5 | Getting RTC set up on machine
2016-02-09 | 17:00 | 17:30 | 0.5 | Discussing when to work on project and who to talk to
2016-02-09 | 17:30 | 18:30 | 1 | Figuring out log-in information and downloading necessary programs.
2016-02-10 | 10:00 | 12:00 | 2 | In-depth discussion with Ryan (resident RTC expert) on the inner workings of RTC and the ALM suite. It streamlines Git, JIRA, DOORS, Dimensions, and other things!
2016-02-11 | 11:00 | 17:30 | 6.5 | Investigation into how RTC works and how to pull from our version of it. Figured out basic commands for pulling from a stream.
2016-02-12 | 10:30 | 18:30 | 8 | Began experimenting with dummy system to pull data from RTC into the Task Management System.
2016-02-15 | 9:15 | 15:05 | 5.8333 | Adding component to ensure that dependencies are loaded correctly for RTC.
2016-02-16 | 9:00 | 14:00 | 5 | Various RTC related things
2016-02-16 | 16:00 | 17:00 | 1 | Meeting for RTC update and path forward for what we want to do and how we want to do it.
2016-02-17 | 9:00 | 17:00 | 8 | Page Navigation
2016-02-18 | 9:00 | 17:00 | 8 | Page Navigation
2016-02-19 | 9:00 | 17:00 | 8 | Page Navigation
2016-02-22 | 9:00 | 12:00 | 3 | Finished Page Navigation
2016-02-22 | 12:00 | 15:00 | 3 | Working on presentation 1
2016-02-22 | 15:30 | 16:30 | 1 | Presenting
2016-02-23 | 9:00 | 16:00 | 7 | Working on stream pull functionality
2016-02-24 | 9:00 | 17:00 | 8 | Working on stream pull functionality
2016-02-25 | 9:00 | 17:00 | 8 | Working on stream pull functionality
2016-02-26 | 6:45 | 8:00 | 1.25 | Presenting initial demo of stream pull functionality
2016-02-26 | 8:00 | 9:00 | 1 | Touch-ups and troubleshooting.